## Slide 1
FNIIP/AIIP: Capital Projects Priority List
Step-by-Step Guide
OFA Capital Planning Session January 13, 2026
Presented by: Mark Bellefleur, Senior Engineer, Indigenous Services Canada

## Slide 2
Purpose
To provide step-by-step guidance to complete the First Nation Infrastructure Investment Plans (FNIIP) or the Agency Infrastructure Investment Plans (AIIP) under the Ontario Final Agreement (OFA)

## Slide 3
First Nation Child and Family Services (FNCFS) capital requests in Ontario will follow an established planning process
FNCFS capital will be integrated into overall community infrastructure planning to ensure alignment with broader community goals
First Nations will identify their FNCFS capital needs in their FNIIPs and FNCFS Agencies will identify their FNCFS capital needs in their AIIPs (submitted 6 months after OFA effective date in the first year, and in the fall in subsequent years)
ISC will assess the eligibility of FNCFS capital proposals and prioritize projects for funding using the OFA FNCFS Priority Ranking Framework
OFA Capital Planning

## Slide 4
Part A:
Privacy Statement
First Nation Contact Information and Authorization (FNIIP)
Agency Contact Information and Authorization (AIIP)
Part B:
First Nation Capital Project Priority List (FNIIP)
FNCFS Agency Capital Project Priority List (AIIP)
FNIIP/AIIP

## Slide 5
Privacy Act Tab – First Nations

## Slide 6
Privacy Act Tab - Agencies

## Slide 7
Part B – Capital Project Priority List

## Slide 8
Use whole, unique numbers starting at 1
Rank multiple FNCFS projects in order
AGENCIES: Ensure alignment with Community Well-Being Plan
Recipient Priority

## Slide 9
Use short, descriptive titles
Include infrastructure type and phase
Ex: Healing Lodge – Feasibility Study
Project Name

## Slide 10
Summarize scope, purpose, phase
1
Explain link to FNCFS service delivery
2
Note needs assessment or cultural supports
3
Project Description

## Slide 11
A summary of the scope of work and intended outcomes of the project
It should capture the project's purpose, phase, and connection to FNCFS objectives
Required information/steps:
    Identify whether the project is for feasibility, design, new build, or renovation
    Clearly state how the project supports the delivery of FNCFS services
    Include whether the project has completed a needs assessment or is being designed to support culturally appropriate services
Project Description

## Slide 12
Add contextual notes or status info
Indicate new/existing building and infrastructure availability
Ex: BCR submitted, needs assessment completed
Comments

## Slide 13
A space for contextual notes, supporting information, or cross-references that provide clarity or important caveats
Required information/steps:
  Include relevant status (e.g. “ready to proceed,” needs assessment underway, etc.)
  New or Existing Building
  Building Inspection Completed and condition (Closed, Poor, Fair Good, New)
  If existing building, does it meet building codes?
  If existing building, estimated percentage of building that can meet service delivery needs?
  Are there any other assets in the community, within an hour, or over an hour away that deliver these services? Indicate time
  How many FNCFS services will be delivered in this building? Indicate all services
  Is the building shared or will be used entirely for FNCFS? If shared, indicate percentage used
  Infrastructure present or not (Watermain, sewer main, storm if applicable, hydro/electrical)
Comments

## Slide 14
A classification that aligns with ISC infrastructure reporting categories for planning and funding purposes
This field allows requests to be easily sorted for application of the Priority Ranking Framework
Reflects current phase you are applying for
This is a dropdown list in the FNIIP/AIIP
    For example:
    FNCFS Facility – Feasibility
    FNCFS Facility – Design
    FNCFS Facility – Construction
Project Category

## Slide 15
All-inclusive project cost
Auto-populated from fiscal year entries
Use whole-dollar Canadian amounts
Total Estimated Cost

## Slide 16
List external confirmed or anticipated funds
Include FN, CMHC, provincial, or philanthropic contributions
Enter $0 if none
Shared Costs (Excluding ISC)

## Slide 17
Enter requested ISC amount per fiscal year
Ensure totals equal full project cost
Smaller projects may require only one fiscal year
ISC Funding Request – FY

## Slide 18
Examples / Sample FNIIP / AIIP
Sample Walkthrough of Templates:
2026-2027 FNIIP Sample Template - OFA
2026-2027 AIIP Sample Template - OFA

## Slide 19
For more information about the implementation of the OFA’s FNCFS capital commitment or the OFA Capital Process, you can contact: immobilisation-edon-onfa-capital@sac-isc.gc.ca
Contact Information

## Slide 20
Thank you! – Merci! – Miigwech!